## Original
Weeks
| J | Feb |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  |  | Sept
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
Project Kick-off | ◊
Project Planning
Literture Review
System Familiarisation
Design emotional behaviours
Implement emotional behaviours
Experiment Design
Test & update emotional behaviours | [20 empty] | ◊
Ethics Application & Processing | [25 empty] | ◊
Experiment | [28 empty] | ◊
Results Analysis & Write Up
Hand in | [33 empty] | ◊

## Live
Weeks
| J | Feb |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  |  | Sept
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
Project Kick-off | ◊
Project Planning
Literture Review
System Familiarisation
Design emotional behaviours
Implement emotional behaviours
Experiment Design
Test & update emotional behaviours | [20 empty] | ◊
Ethics Application & Processing | [25 empty] | ◊
Experiment | [28 empty] | ◊
Results Analysis & Write Up
Hand in | [33 empty] | ◊